## Cover
Estimation - Startup Database Project
Ver. No. | Ver. Date | Prepared By | Reviewed By | Description
V1.0 | 2017-11-29 | PwC SDC | PwC SDC
WARNING: The following disclaimer and copyright notices must be customised for your local territory - if you need assistance with appropriate wording, contact your local Risk Management or Office of General Counsel. This publication has been prepared for general guidance on matters of interest only, and does not constitute professional advice. You should not act upon the information contained in this publication without obtaining specific professional advice. No representation or warranty (express or implied) is given as to the accuracy or completeness of the information contained in this publication, and, to the extent permitted by law, PricewaterhouseCoopers Information Technologies (Shanghai) Co., Ltd.. & PricewaterhouseCoopers Service Delivery center (Bangalore) Pvt Ltd., its members, employees and agents do not accept or assume any liability, responsibility or duty of care for any consequences of you or anyone else acting, or refraining to act, in reliance on the information contained in this publication or for any decision based on it. © 2017 PricewaterhouseCoopers Information Technologies (Shanghai) Co., Ltd.. & PricewaterhouseCoopers Service Delivery center (Bangalore) Pvt Ltd.. All rights reserved. In this document, “PwC” refers toPricewaterhouseCoopers Information Technologies (Shanghai) Co., Ltd.. & PricewaterhouseCoopers Service Delivery center (Bangalore) Pvt Ltd. which is a member firm of PricewaterhouseCoopers International Limited, each member firm of which is a separate legal entity.

## Summary1 (hidden)
Tasks | Effort Estimation |  | Note
| Man hours | Man days
Mobile UI Development | 2432 | 304
Backend | 1400 | 175
After Go Live Support | 0 | 0
Testing | 1824 | 228
Total | 5656 | 707
Phase1 - UI & backend | 1680 | 210
Phase2 - UI & backend | 1320 | 165
Total Dev | 3000 | 375

## Assumption
General Assumptions
1. 外部数据接入： 除了PwC内部数据，包括行业分析数据，初创公司，大投资机构基本信息，行业周报，订阅推送等等都依赖于第三方输入。比如烯牛
2. 由于对接哪些PwC 内部系统还不确定，所以对接PwC内部数据库和数据清洗，整合，归纳整理的effort暂不包含在此次估算里面。
3. “发现独角兽”的分析模型由PwC China完成，所需时间不在此次估算里面。
其他前端呈现的前提假设如下：
1. 移动App只支持手机端和Apple iPad，不包括Android Tablet和Web
2.支持iPhone 9.0以上版本，安卓5.0 以上版本，不支持Android tablet。Android，iOS和iPad会使用同一套界面设计
3.估算中包含了2周UAT支持的工作量，如果实际情况不同，可按实际情况做调整。
4.Apple开发者账号将由GTS提供
5.UI/UX设计，BA只有概要估算
6.用户消息通知Android采用国内厂商（如极光），苹果采用APNS
7.App只支持中文，不支持多语言界面
8.只支持手机竖屏

## Summary
| Tasks | Effort Estimation |  | Note
|  | Man hours | Man days
| Mobile UI Development | 2432 | 304
| Backend | 1400 | 175
| After Go Live Support | 0 | 0
| Testing | 1824 | 228
| Total | 5656 | 707
| Phase1 - UI & backend | 2600 | 325
| Phase2 - UI & backend | 1232 | 154
| Total Dev | 3832 | 479
Implementation | Mobile UI Development | Backend Development | Testing | Estimated Months - 2 UI dev - 1 Backend - 1 tester
Phase1 | 136 | 74 | 102 | 3.5455
Phase2 | 102 | 63 | 76.5 | 2.7443
Phase3 | 66 | 38 | 49.5 | 1.7443
BA | 51 |  |  | 0.57955
UX | 64 |  |  | 0.72727
Grand Total | 822 |  |  | 9.3409

## Effort Estimation
ID | Features | Sub Feature | Description | Phase | Android Effort (Man day) | iOS Effort (Man day) | Backend Service (Man day) | Data Source | Comment
1 | App/Web架构设计
1.1 | Mobile/Web架构设计 |  | 包括基础框架设计和环境搭建 | Phase1 | 5 | 5 | 5
2 | 订阅
2.1 | 行业/关键字（领域） |  | 接口提供热门关键字 | Phase1 | 3 | 3 | 3 | 外部数据源
2.2 | 公司订阅 |  |  | Phase1 | 4 | 4 | 5 | 外部数据源
2.3 | 主题订阅 |  |  | Phase2 | 5 | 5 | 5 | 外部数据源
2.5 | 查看我的订阅／追踪 |  |  | Phase1 | 3 | 3 | 3 | 外部数据源
2.6 | 查看我的收藏 |  |  | Phase1 | 3 | 3 | 3 | 外部数据源
2.7 | 按公司名称搜索 |  | search list | Phase1 | 3 | 3 | 5 | 外部数据源
3 | 内容推送
3.1 | 内容列表 | 新闻 | 推送／列表内容仅基于文字，图片，URL链接； | Phase1 | 3 | 3 | 3 | 外部数据源
|  | PwC合作关系更新 |  | Phase3 | 3 | 3 | 3 | 内部分析 | 这条估算仅包含分析结果展示，不包含分析模型建立的时间
|  | PwC观点／视点 |  | Phase2 | 3 | 3 | 3 | 内部数据接入
|  | 智能推送（选推） |  | Phase2 | 3 | 3 | 5 | 内部分析 | 这条估算仅包含分析结果展示，不包含分析模型建立的时间
3.2 | 各内容详细页面 |  |  | Phase1 | 2 | 2 | 3 | 外部数据源
4 | 分析报告
4.1 | 潜力公司 | 基于FUX／行业 |  | Phase3 | 3 | 3 | 5 | 内部分析 | 这条估算仅包含分析结果展示，不包含分析模型建立的时间
4.2 | 研报 | Tab列表展示 | 融资事件，知名机构动向 | Phase2 | 4 | 4 | 5 | 外部数据源
|  | 研报详细内容 | 4个模板 | Phase2 | 6 | 6 | 5 | 外部数据源
5 | 行业分析（领域）
5.1 | 行业 | 主界面包括搜索及列表 |  | Phase1 | 5 | 5 | 5 | 外部数据源
5.2 | 热门领域 | 公司列表 |  | Phase1 | 3 | 3 | 3 | 外部数据源
|  | 领域新闻 | 新闻列表和详细 | Phase1 | 4 | 4 | 4 | 外部数据源
|  | 公司分布 | 图表 | Phase1 | 10 | 10 | 5 | 外部数据源
5.3 | 生态圈 future scope | 知识图谱 | 图表 | [5 empty] | 需求暂不明确
上下游
相关技术
合作机构
6 | 客户360跟踪（大客户/EPB）
6.1 | PwC关联信息展示 |  | 客户与PwC相关信息内容展示（比如是否与PwC有过合作等） | Phase3 | 5 | 5 | 5 | 内部数据接入
6.2 | 基本信息 |  | 公司信息 | Phase1 | 2 | 2 | 3 | 外部数据源
|  |  | 工商信息 | Phase1 | 2 | 2 | 3 | 外部数据源
|  |  | 股权结构 | Phase1 | 2 | 2 | 3 | 外部数据源
6.3 | 投资信息 | 投资动向 |  | Phase1 | 2 | 2 | 3 | 外部数据源
|  | 投资图谱 |  | Phase1 | 4 | 4 | 5 | 外部数据源
|  | 投资阶段分析 |  | Phase1 | 4 | 4 | 5 | 外部数据源
6.4 | 未公开投资项目列表 |  |  | Phase2 | 3 | 3 | 5 | 外部数据源
6.5 | 投资事件 |  |  | Phase2 | 3 | 3 | 5 | 外部数据源
6.6 | 团队信息 |  |  | Phase2 | 4 | 4 | 5 | 外部数据源 & 内部数据接入
6.7 | 公司经营状况 |  |  | Phase3 | 4 | 4 | 5 | 内部分析 | 这条估算仅包含分析结果展示，不包含分析模型建立的时间
6.8 | 公司动态 |  | 列表／趋势 | Phase3 | 6 | 6 | 5 | 外部数据源
6.9 | 产品介绍 | 产品列表详细 |  | Phase3 | 4 | 4 | 5 | 外部数据源
|  | 维度行业差异化查询 |  | Phase3 | 4 | 4 | 5 | 内部分析 | 这条估算仅包含分析结果展示，不包含分析模型建立的时间
6.1 | 合作机构 |  | 支持公司提供服务的外围服务提供商 | Phase3 | 4 | 4 | 5 | 内部分析 | 这条估算仅包含分析结果展示，不包含分析模型建立的时间
6.11 | 竞品分析 |  | 图表 | Phase1 | 4 | 4 | 5 | 外部数据源
6.12 | 新闻相关报道 |  |  | Phase2 | 3 | 3 | 5 | 外部数据源
7 | Scout Service
7.1 | 项目列表 |  |  | Phase2 | 5 | 5 | 5 | 内部数据接入
7.2 | 项目活动跟踪 |  |  | Phase2 | 5 | 5 | 5 | 内部数据接入
7.3 | PwC所提供服务列表 |  |  | Phase2 | 4 | 4 | 5 | 内部数据接入
7.4 | 商业计划上传 |  |  | Phase2 | 3 | 3 | 5 | 内部数据接入
8 | Generate FUX（Engine） | [7 empty] | 有PwC China 负责数据准备，清洗，归纳，和数据模型分析的建立 SDC 只需要将分析结果(推荐新兴公司）的展示到前端 因业务计算逻辑不明确，无法进行估算
8.1 | Recruiting size |  |  |  | - | -
8.2 | Reported by social media |  |  |  | - | -
8.3 | Recently invited by investor |  |  |  | - | -
8.4 | personel analysis |  |  |  |  | -
8.5 | risk assessment framework |  |  |  | - | -
|  |  | Total |  | 152 | 152 | 175
|  |  | Phase1 |  | 68 | 68 | 74
|  |  | Phase2 |  | 51 | 51 | 63
|  |  | Phase3 |  | 33 | 33 | 38

## Screenshot
No. | 功能 |  | 网页地址 | 截图
1 | 公司Profile | Startup
|  | 大企业 - EPB - Investor - | http://www.xiniudata.com/#/investor/217/overview
2 | 行业、领域 |  | http://www.xiniudata.com/#/industry/280/overview
3 | 研报 |  | http://www.xiniudata.com/#/blog/5a0127dad4225f03d51d8bad/detail

## Mobile UI Estimation (hidden)
ID | Features | Sub Feature | Description | Phase | Android Effort(Man day) | iOS Effort(Man day) | Backend Service(Man day) | Comment
1 | App/Web架构设计
1.1 | Mobile/Web架构设计 |  | 包括基础框架设计和环境搭建 | Phase1 | 5 | 5
2 | 订阅
2.1 | 行业/关键字（领域） |  | 接口提供热门关键字 | Phase1 | 3 | 3
2.2 | 公司订阅 |  |  | Phase1 | 4 | 4
2.3 | 主题订阅 |  |  | Phase1 | 5 | 5
2.5 | 查看我的订阅／追踪 |  |  | Phase1 | 3 | 3
2.6 | 查看我的收藏 |  |  | Phase1 | 3 | 3
3 | 内容推送
3.1 | 内容列表 | 新闻 | 推送／列表内容仅基于文字，图片，URL链接； | Phase1 | 3 | 3
|  | PwC合作关系更新 |  |  | 3 | 3
|  | PwC观点／视点 |  | Phase1 | 3 | 3
|  | 智能推送（选推） |  | Phase1 | 3 | 3
3.2 | 各内容详细页面 |  |  | Phase1 | 2 | 2
4 | 分析报告
4.1 | 潜力公司 | 基于FUX／行业 |  |  | 3 | 3
|  | 按公司名称搜索 | search list |  | 3 | 3
4.2 | 研报 | Tab列表展示 | 融资事件，知名机构动向 | Phase1 | 4 | 4
|  | 研报详细内容 | 4个模板 | Phase1 | 6 | 6
5 | 行业分析（领域）
5.1 | 行业 |  | 主界面包括搜索及列表 | Phase1 | 5 | 5
5.2 | 热门领域 | 公司列表 |  | Phase1 | 3 | 3
|  | 领域新闻 | 新闻列表和详细 | Phase1 | 4 | 4
|  | 公司数据 | 图表 | Phase1 | 10 | 10
5.3 | 生态圈 Phase2 scope | 知识图谱 | 图表
上下游
相关技术
合作机构
6 | 客户360跟踪（大客户/EPB）
6.1 | PwC关联信息展示 |  | 客户与PwC相关信息内容展示（比如是否与PwC有过合作等） |  | 5 | 5
6.2 | 基本信息 |  | 公司信息 |  | 2 | 2
|  |  | 工商信息 |  | 2 | 2
|  |  | 股权结构 |  | 2 | 2
6.3 | 投资信息 | 投资动向 |  |  | 2 | 2
|  | 投资图谱 |  |  | 4 | 4
|  | 投资阶段分析 |  |  | 4 | 4
6.4 | 未公开投资项目列表 |  |  |  | 3 | 3
6.5 | 投资事件 |  |  |  | 3 | 3
6.6 | 团队信息 |  |  |  | 4 | 4
6.7 | 公司经营状况 |  |  |  | 4 | 4
6.8 | 公司动态 |  | 列表／趋势 |  | 6 | 6
6.9 | 产品介绍 | 产品列表详细 |  |  | 4 | 4
|  | 维度行业差异化查询 |  |  | 4 | 4
6.1 | 合作机构 |  |  |  | 4 | 4
6.11 | 竞品分析 |  | 图表 |  | 4 | 4
6.12 | 新闻相关报道 |  |  |  | 3 | 3
7 | Scout Service
7.1 | 项目列表 |  |  |  | 5 | 5
7.2 | 项目活动跟踪 |  |  |  | 5 | 5
7.3 | PwC所提供服务列表 |  |  |  | 4 | 4
7.4 | 商业计划上传 |  |  |  | 3 | 3
8 | Generate FUX（Engine）
8.1 | Recruiting size |  |  |  | - | -
8.2 | Reported by social media |  |  |  | - | -
8.3 | Recently invited by investor |  |  |  | - | -
8.4 | personal analysis |  |  |  |  | -
8.5 | risk assessment framework |  |  |  | - | -
|  |  | Total |  | 152 | 152 | 0

## Baseline (hidden)
Development Estimation Baseline Data
Layer | Estimation Item | Description | Effort (Hour)
|  |  | L | M | H
Server Side | Data | Reflects the data logic complexity | 6 | 12 | 18
| Business Logic | User identifiable group of logically related data or control information maintained within the boundary of the application. | 6 | 12 | 18
| Pages | Responsive pages that support IOS, Android and Web accesses with common resolutions. | 4 | 8 | 12
| Configuration | Includes configuations for server, website and communication etc. | 4 | 6 | 8
Mobile App | Mobile App UI Screen | Native UI Screen Development | 8 | 24 | 40
| Mobile App Business Logic | Business Logic for the presenting the data in UI including the Cache/transformation of the Data | 8 | 16 | 24
| Mobile App Service Integration [REST API] | This calls the backend REST API | 8 | 16 | 24
User Experience + Visual Design | - |  | 5 | 15 | 25

## ResourcePlan (hidden)
High Level Project Plan
| Project Role | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | Total Effort (Manday) | Total Effort (Hours)
Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0